Project Initiation and Planning
Project: Hospital Operations
Date: July 2026

Project Initiation and Planning

Task 1.

Introduction
The hospital is facing delays in patient management, outdated record-keeping systems, and inefficient communication between the departments (for example, admissions, doctors, and pharmacy).
You will define the scope of the analysis and identify the core business problems.

Problems identified
The hospital is facing long patient waiting times, outdated records which is probably written records, paper based, or bad record keeping system. There is also bad communication between the departments ( admissions, doctors etc.)
In conclusion, The hospital is currently facing inefficiencies in patient flow and administrative coordination due to outdated systems and communication gaps. These issues result in long wait times, patient dissatisfaction, and increased staff workload.

Step 2 : Stakeholder Chart ( completed in Excel)

Step 3: Step 3: Define Objectives and Scope
Project Objectives:
- Reduce patient wait times by streamlining admissions and discharge processes.
- Improve inter-department communication and handoffs.
- Upgrade record-keeping to a digital hospital management system.
- Enhance overall patient experience.
 Scope of the Project:
- Departments involved: Admissions, Medical (Doctors & Nurses), IT, Pharmacy, Administration
- Functions analysed: Patient registration, record updates, internal communication, discharge process.
- Systems impacted: Paper records, EMR software, inter-department workflows

Task 2.
Conduct Stakeholder Interview Questions. ( Focusing on Specific Areas)

Hospital Admin
- What are the current bottlenecks in patient management and operational decision-making?
- What key metrics do you use to measure hospital performance?
Doctors and Nurses
- How do delays in patient record updates affect patient care?”
- What functionalities in the current record-keeping system hinder your efficiency?
IT department
- What are the limitations on the current systems and what upgrades are needed?
- How would you rate the systems reliability and how easy it is to maintain?
Pharmacy staff
- How does communication delays impact medication dispensation?
- What integration between departments would help improve workflow?
Patient
- How do you feel about the wait time and communications during your hospital visit?
- What improvements would you like to see in managing your appointments and records?
Insights
- Take detailed notes of each interview
- Asked to provide examples
- Keep it all in one spreadsheet or template
- Record their concerns and their suggestions

Step 2 . Business Requirement Document
TOC

Contents

# 1.Introduction:
The hospital is experiencing inefficiencies Due to outdated patient record systems long patient wait times and poor communication between the department such as admissions medical pharmacy and diet project aims to address these challenges through process optimization and technology upgrades.
# 2.Purpose of the Document
This business requirement document outlines the business requirements for improving hospital operations. It defines the current pain points, desired improvements, functional and non-functional requirements and the overall scope of the project.
# 3.Project Scope
In scope:
- Patient admissions and discharge processes
- Inter-department communications ( Doctors, Nurses, Admissions, IT, Pharmacy)
- Patient record management systems ( digital transformation)
Out of Scope:
- Clinical Procedures
- external vendor procurement process
## 4.Stakeholders
Name	Role	Department
Hospital Director	Project Sponsor	Administration
Dr. Khan	Senior Consultant	Medical
Nurse Aisha	Head Nurse	Medical
Mr. Shah	IT Manager	IT
Mrs. Patel	Lead Pharmacist	Pharmacy

## 5.Business Objectives
- Produce reduce patient wait times by 20% within six months
- re digitise patient records to eliminate paper based systems improve communication and coordination across the department's
- enhance patient experience and stuff efficiency
# 6.Functional Requirements
ID	Requirement Description
FR1	Implement the centralised electronic medical transport system accessible hospital wide intentions
FR2	Enable real time status updates between departments (patient admitted, seen discharged)
FR3	automate appointment booking and registration process
FR4	Integrate pharmacy with patient discharge workflow to prepare prescriptions in advance

# 7.Non Functional Requirements
ID	Requirement Description
NFR1	System must comply with healthcare data protection regulation ( e.g. HIPAA/GDPR)
NFR2	EMR system should have 99.9% uptime and support role -based access control
NFR3	Solution must be user- friendly with minimal training required
NFR4	Ensure data backup, encryption, and recovery mechanisms

## 8.Current challenges/Pain points
- Patient records are manually updated, leading to delays and errors
- pharmacy receives discharge notices late, delaying medication processing
- no centralised communication platform for real time updates between department's
- long wait times for patients due to inefficient handovers
## 9.Proposed improvements
- introduce an integrated EMR system to eliminate manual record keeping
- motivate communication alerts and patient status updates
- improve data sharing between IT systems used by different departments
- train staff to adopt new digital tools effectively
## 10.success criteria
- 20% reduction in patient wait times
- 100% of patient records digitised within three months
- 90% satisfaction rate from staff on new system usability
- zero major security breaches post implementation
## 11.Assumptions
- all departments are willing to adopt digital systems
- necessary hardware and Internet infrastructure is in place
- budget approval will be granted for technology upgrades
## 12.constraints
- limited budget for IT investment
- stop availability for training during working hours
- compliance with national healthcare data laws
## 13.Dependencies
- selection and onboarding up an EMR vendor
- collaboration with it for infrastructure readiness
- coordination with HR for staff training

# 14. Gap Analysis and prioritization
## 14.1Gap analysis
This analyses compares the current state of the hospital operations to the desired future state
Process Area	Current State	Future State	Gap	Action Needed
Patient Admissions	Manual paperwork; long wait times	Online pre-registration; digital check-in	Lack of automation, time consuming	Implementation digital admission forms and self-check in kiosks
Patient Record Keeping	Paper based or fragmented EMR system	Centralised EMR system accessible by all departments	Records not updated in real-time	Deploy integrated EMR system across departments
Inter-departmental Communication	No centralised platform; delays in communication	Real- time digital communication between departments	Delays in sharing patient status, test results, discharge info	Integrate communication tools into hospital workflow system
Discharge and Pharmacy	Discharge paperwork delays pharmacy processing	Automated notification to pharmacy upon discharge	No linkage between discharge and pharmacy processes	Develop integration between EMR and pharmacy systems

# 15. Prioritization table
Below is a prioritization table where I have prioritized BRD requirements based on:
- Business Impact
- Feasibility
- Cost or effort

Requirements ID	Requirement	Business Impact	Feasibility	Priority	Reasoning
FR1	Centralised EMR system	High	Medium	High	Core to addressing communication and records
FR3	Automated patient registration	High	High	High	Reduces wait time significantly
FR4	Integration of pharmacy with discharge process	Medium	Medium	Medium	Improves discharge efficiency
NFR1	Compliance with healthcare regulations	High	High	High	Mandatory for implementation
NFR3	User friendly interface	Medium	High	Medium	Important for adoption by staff

# 16. Solution Design
## 16.1. Develop Process Flows
Link: https://lucid.app/lucidchart/b9c9205d-568a-4807-b0cd-8279b7f12491/edit?beaconFlowId=19C53F63F19A33A5&invitationId=inv_f439e105-9f74-42ce-86f7-e383b24399ff&page=m-5o7ONTd-nK#

Technology assessment:
Organization: Medium sized hospital
Assessment date: 11/08/2025
Assessor: Ume Laila Batool

# 17.Current Technology Landscape

Area	Current Technology	Issues/Limitations
Patient Records	Paper-based + basic desktop system	Delays, prone to errors, not accessible remotely
Communication	Email, landline phones	Slow, fragmented, no real-time updates
Scheduling	Manual booking ledger	Double bookings, missed appointments
Pharmacy Orders	Paper prescriptions	Delays in medication dispensing, miscommunication
Reporting	Manual spreadsheets	Time-consuming, difficult to consolidate

# 18. Recommended Upgrades
Area	Recommended Technology	Benefits
Patient Records	Electronic Medical Records (EMR) system	Centralized, real-time updates, accessible across departments
Communication	Integrated secure messaging app	Faster, HIPAA-compliant, reduces delays
Scheduling	Digital scheduling software integrated with EMR	Avoids double bookings, improves resource allocation
Pharmacy Orders	EMR-linked e-prescription system	Reduces errors, faster turnaround
Reporting	Business Intelligence (BI) dashboard	Real-time performance metrics, easier decision-making

# 19. Integration Considerations
- Data migration from paper to EMR
- Staff training on EMR and messaging tools
- Security compliance with healthcare regulations (HIPAA)
- Hardware upgrades (computers, tablets, Wi-Fi infrastructure)

# 20. Estimated Implementation Timeline
Phase	Duration
Vendor selection & procurement	2 months
Data migration	3 months
Staff training	1 month
System go-live & monitoring	1 month

# 21. Solution Evaluation
## Solution Evaluation Metrics

Metric	Baseline (Before Implementation)	Target (After Implementation)	Measurement Method	Frequency
Average patient wait time	90 minutes	70 minutes (↓ 20%)	EMR timestamp logs	Monthly
Record update time	24 hours	Real-time	EMR audit reports	Weekly
Communication delay between departments	Avg. 2 hours	< 15 minutes	Internal messaging logs	Weekly
Appointment no-show rate	15%	10%	Scheduling software reports	Monthly
Prescription error rate	5%	< 1%	Pharmacy error reports	Quarterly
Staff satisfaction	60%	80%	Staff surveys	Quarterly
Patient satisfaction	70%	85%	Patient feedback forms	Quarterly

# 22.Evaluation Process
1. Baseline Data Collection – Use existing hospital records to capture current performance levels before system changes.
2. Post-Implementation Monitoring – Track metrics using the EMR, scheduling software, and surveys.
3. Stakeholder Review Meetings – Monthly sessions with department heads to review results and identify any adjustments needed.
4. Continuous Improvement Loop – Use feedback to fine-tune processes and system features.